## Sheet1
Vision:
To develop a responsive and efficient JavaScript-based reminder bot called tSunade_Bey that assists users in managing tasks and reminders with ease and style.
Backlog:
Priority | User Story/Feature | Description | Estimate (Story Points)
High | User Authentication | Allow users to sign up, log in, and log out. | 5
High | Set Reminders | Users can set reminders with a date and time. | 8
High | Notification System | Send out notifications when a reminder is due. | 8
Medium | Personalize Reminders | Add custom notes or themes to reminders. | 3
Medium | Recurring Reminders | Option to set daily, weekly, or monthly reminders. | 5
Low | Bot Settings | Customize notification sounds, snooze times, etc. | 4
High | Dashboard | A user-friendly interface to view and manage reminders. | 8
Medium | Bot Integration | Integrate with chat platforms like Slack or Teams. | 5
Low | Analytics | Track reminder completion rates and user activity. | 4
Medium | Multi-language Support | Support reminders in multiple languages. | 7
Epics:
User Management: Includes User Authentication.
Reminder Core Functions: Comprises Set Reminders, Recurring Reminders, and Notification System.
Enhancements: Covers Personalize Reminders, Bot Settings, and Multi-language Support.
Integration & Analytics: Encompasses Dashboard, Bot Integration, and Analytics.
Remember, this is a basic structure. As the project evolves, you might want to add more details, adjust priorities, or re-estimate story points. Always keep the communication channels open with stakeholders and your ninja squad (the development team). 🍃🔥🌊🌪️
🌐 Sources
General knowledge on Agile and Backlog Creation.